## Wedding Plan
Hotel Bell Classic_WEDDING PARTY PLAN
2026 年 6 月 21 日 ( 日曜日 ) |  |  | ヘアメイク後撮影 | あり
|  |  | 記念撮影 | Amore Wedding Tokyo
|  |  | スナップ | Amore Wedding Tokyo
フリガナ | フリガナ |  |  |  | 大人 | 90 名様
新郎 Tint Htoo Aung 様 | 新婦 Ei Phyu Win 様 |  | VTR撮影 | Amore Wedding Tokyo | 担当 | May
[5 empty] | MC | Antt Minn
時間 | 進行 | 場所 | 内容 |  | BGM |  | スタッフ
15:20 | Guest Reception | ロビー | 15:30 First meet — Video & Photo team on standby. Venue setup: banner posters, tent cards, small tables, DMC QR code cards at each seat.
15:50 | Group Photo 2F | 2F | 15:45 — 2F group photo with guests
16:15 | Chapel Photoshoot | チャペル | 16:10~16:30 chapel photoshoot — then couple rests
16:35 | MC Preparation & BGM Confirm | 会場内 | 16:00 MC spare check / 16:30 MC confirm BGM. Confirm Type-C BGM for opening slideshow & entrance.
16:50 | Waiting for Entrance | バックステージ
17:00 | Slideshow | 会場（スクリーン） | BGM: Type-C. Slideshow of couple's lifestyle photos & highlight video — plays before entrance begins. |  | ① Type-C
17:05 | Groom Entrance with Friends 🎭 | 1F 会場 | BGM: Type-C entrance. Groom enters with friends one by one → waits at centre of floor. |  | ② Groom Entrance BGM (Type-C) |  | 🎤 Announce groom's entrance with energy. Wait for groom to reach centre floor before moving on. 📸 Position at 1F entrance. Capture groom walking in with friends — wide group shot then close-up on groom's face. VTR rolling. 💡 Spotlight tracking groom from entrance to centre floor. Dim main hall for dramatic effect.
17:10 | Bride Entrance with Father — Handover 🎭 | バージンロード | Bride enters with father → father handover to groom |  | ③ Bride Entrance BGM |  | 🎤 Pause and give space at father handover — do not rush this moment. 📸 One photographer at end of Virgin Road (stage side). Key shot: father's expression at handover. VTR: capture full walk. 💡 Warm spotlight tracking bride from entrance to stage.
17:15 | Together — Virgin Road 🎭 | バージンロード |  |  | ④ Virgin Road BGM
17:20 | Ceremony 🎤 🎭 | ステージ | 15 min. Tint Htoo Aung (groom) has active role. Mg Mg Phyo officiating — 3 people on stage. |  |  |  | 🎤 Groom (Tint Htoo Aung) has an active speaking role — confirm his cues beforehand. Officiant: Mg Mg Phyo. 📸 Cover: officiant, couple's expressions, and any ring/vow moment close-ups. VTR rolling throughout. 3 people on stage. 💡 Steady, bright, even lighting throughout ceremony. No dramatic changes.
17:35 | Kanpai — Welcome Toast 🎤 🎭 | ステージ | Friend (Mg Mg Phyo) gives welcome speech → Kanpai toast.
17:40 | Cake Cutting — First Bite, First Kiss & Rings 🎭 | ステージ | Sequence (venue confirmed): Cake cutting → First bite (groom feeds bride) → Ring reveal to guests → First kiss. |  | ⑤ Cake BGM |  | 🎤 Narrate each step and build anticipation. Count down before first kiss. 📸 4 key shots in sequence: (1) knife on cake, (2) first bite — get both faces, (3) ring reveal — shoot from above/front, (4) first kiss. Do NOT miss ring reveal! 💡 Bright stage lighting. Flash-friendly.
17:50 | Couple Exit — Flash Phone Lights 🎭 | 1F 会場 | Guests hold up phone flashlights to send off couple for costume change. Groom's 2nd outfit: T-shirt + coat.
17:55 | Chuza Entertainment — Game Paper, Glow Sticks & AI Movie | 会場 | Distribute game quiz paper + glow sticks to ALL guests. AI/profile video plays simultaneously. Photographer takes table photos during this time.
18:10 | Re-entrance — Laser Show, Stairs & Love Speech 🎭 | 2F ギャラリー | Laser show → couple descends from 2F Gallery stairs → Love speech (guests hold lit glow sticks). BGM: Sweet Heart. |  | ⑥ Sweet Heart |  | 🎤 Build crowd energy before laser show starts. Cue music (Sweet Heart). Let love speech breathe — do not interrupt. 📸 VTR: wide shot from 2F showing laser show + staircase descent. Snapshot: couple's faces + full crowd with glowing sticks. 💡 Laser show sequence on cue. After descent, transition to warm romantic lighting for love speech.
18:20 | Guest Speeches — Father & Friends 🎤 🎭 | ステージ | 1–2 groups (father's side + friend's side). Each group within 5 min. MC to introduce each speaker. Couple stands at front of stage.
18:30 | Game — MC Quiz 🎤 🎭 | ステージ | 10 questions about the couple (use the game paper distributed during 中座). Guests with 5+ correct answers win a prize — couple provides prizes. Confirm rehearsal & sound check with MC.
18:45 | Round Table Photo | 各テーブル | Couple visits each table for photos. Table layout: approx. 10 round tables × 30 guests / 9 round tables × 36 guests. Photographer covers all tables.
19:00 | Letter to Family — Bride 🎤 🎭 | ステージ | Bride reads letter to family with soft backing BGM. Tech: cue music at the start. Tissues ready. |  |  |  | 🎤 Stand by but remain silent. Cue backing BGM softly at the start of reading. 📸 Capture bride reading + family members' reactions. Be discreet — no flash. VTR: steady wide shot. 💡 Soft warm lighting only. Reduce brightness.
19:05 | Thank You Message — Groom 🎤 🎭 | ステージ
19:10 | Flower Shower 🎭 | 1F 会場 | Key highlight moment. Couple walks through flower shower from guests. |  | ⑦ Flower Shower BGM |  | 📸 Wide shot of full shower + close-up of couple's faces. VTR: overhead angle if possible. This is a key highlight moment. 💡 Full bright warm lighting — joyful and celebratory.
19:15 | Bouquet Toss from Stairs 🎭 | 2F 階段 | Bride throws bouquet from top of 2F Gallery stairs down to guests at ground floor. |  |  |  | 🎤 Gather single women to the floor. Build excitement with countdown. 📸 Split: one photographer on stairs with bride, one in crowd below. Capture the toss arc + catch moment.
19:25 | Group Photo | 会場 | All guests + couple + family. Photographer coordinates positioning.
19:35 | Depart — Both Together 🎭 | 1F 出口 | Both exit together through 1 door. Guests line both sides and applaud/wave. |  | ⑧ Departure BGM
19:40 | Lobby — Petit Gift Farewell | ロビー | Couple stands at lobby entrance, gives petit gift to each departing guest. Photographer captures farewell moments. Party closes at 19:30.